## README
DSM Schedule Navigator: Assumptions Workbook
Independent concept by John Seggman. Illustrative, industry-typical values only. Contains no proprietary data.
How it works | Edit the green-tinted cells on any sheet, save, then drag this file onto DSM Schedule Navigator (or use Load workbook). The app rebuilds the schedule, propagates delays, and raises flags.
Settings | Status date (the 'now' line), polishing template, Monte Carlo runs, random seed.
Process_Template | Ordered unit operations, seed train through bulk fill. Durations are min / likely / max hours (used for Monte Carlo). Set Enabled = N to drop a step. Category = Polishing rows are arranged by the selected polishing template.
Polishing_Options | Polishing sequences. A = AEX flow-through then CEX bind/elute. B = CEX then HIC. C = three-step. Pick the active one in Settings.
Equipment | Every vessel and skid per building with cleaning / changeover turnaround. Adding a second capture skid adds parallel capacity automatically.
Mass_Balance | Titer, step yields, and Protein A column sizing per product. Protein A duration and DS output are computed from these.
Campaign_Plan | Campaigns by building: product, client, QC release and handoff-to-DP days. Batch count, first thaw and cadence generate batches only for campaigns with no Batch_List rows.
Batch_List | One row per batch: requested thaw, DP Need Date, status, optional bioreactor. Paste rows from 'Plan a campaign' in the app. Edit a date to move a batch; set Status to Hold or Cancelled.
Hold_Limits | Maximum (and minimum) wait between a step and the next. These drive red / yellow hold-time flags.
Flag_Rules | Thresholds for red and yellow flags. Change a threshold to tune sensitivity.
Resources | Operators per shift per building and area. Used to flag shifts where planned work exceeds crew.
Materials | Consumables and resin life. Flags shortages against the scheduled batches and reorder lead time.
Calendar | Site holidays. Steps marked 'Weekday start only' will not start on weekends or holidays.
Events | Live deviation / delay log. Set Active = Y and reload. Types: Delay, Equipment down, Batch lost, Hold extension.
Color key | Green-tinted cells are inputs. Source / Confidence column says where each default came from.

## Settings
Setting | Value | Unit | Notes
Status date | 2026-11-17 07:00 | date-time | The 'now' line. Steps that started before this are locked.
Polishing template | A | A / B / C | See Polishing_Options
Monte Carlo runs | 500 | runs | Triangular sampling of min / likely / max durations
Random seed | 42 |  | Same seed gives repeatable Monte Carlo results
Planning horizon | 120 | days | Timeline length from first thaw
Auto-level future batches | Y | Y / N | Re-plan thaw dates of not-yet-started batches after an event
Planned hold use limit | 50 | % of max hold | When leveling, thaw dates are pushed until planned waits stay under this share of each hold limit

## Process_Template
Seq | Step ID | Step | Stage | Category | Equipment Type | Min h | Likely h | Max h | Duration Basis | Operators | Weekday start only | Critical | Enabled | Notes | Source / Confidence
1 | THAW | Cell bank thaw + shake flask expansion | Seed | Seed | INOC | 240 | 240 | 240 | Fixed | 0.5 | Y | N | Y | Passage every 3-4 d; transfer timed to schedule | Industry typical; replace with site data
2 | N3 | N-3 rocking bioreactor (50 L) | Seed | Seed | N3 | 84 | 84 | 84 | Fixed | 0.5 | N | N | Y |  | Industry typical; replace with site data
3 | N2 | N-2 seed bioreactor (500 L) | Seed | Seed | N2 | 84 | 84 | 84 | Fixed | 0.5 | N | N | Y |  | Industry typical; replace with site data
4 | N1 | N-1 seed bioreactor (4,000 L) | Seed | Seed | N1 | 84 | 84 | 84 | Fixed | 0.5 | N | N | Y | Seed transfers are timed; VCD variation absorbed by split ratio | Industry typical; replace with site data
5 | PROD | Production bioreactor (20,000 L fed-batch) | Upstream | Production | PROD | 312 | 336 | 348 | Fixed | 0.5 | N | N | Y | Day 14 harvest target | Industry typical; replace with site data
6 | HARV | Harvest: disc-stack centrifugation + depth filtration | Downstream | Harvest | HARV | 14 | 18 | 24 | Fixed | 3 | N | Y | Y | Clarified harvest to 2-8 C hold | Industry typical; replace with site data
7 | PROA | Protein A capture | Downstream | Capture | CAPT | 0 | 0 | 0 | ProA cycles | 2 | N | N | Y | Duration = cycles x cycle time + setup | Computed by app from Mass_Balance
8 | VI | Low-pH viral inactivation + neutralization | Downstream | Viral clearance | VIN | 4 | 6 | 8 | Fixed | 2 | N | Y | Y | pH 3.5, 60-120 min hold inside step | Industry typical; replace with site data
9 | VIDF | Depth filtration (post-VI) | Downstream | Viral clearance | FILT | 4 | 6 | 8 | Fixed | 1 | N | N | Y | Removes precipitate after neutralization | Engineer input
10 | POL-AEX | AEX chromatography (flow-through) | Downstream | Polishing | POL | 10 | 14 | 20 | Fixed | 2 | N | N | Y | Removes HCP, DNA, virus | Engineer input
11 | POL-CEX | CEX chromatography (bind/elute) | Downstream | Polishing | POL | 16 | 22 | 30 | Fixed | 2 | N | N | Y | Aggregate and charge variant removal | Engineer input
12 | POL-HIC | HIC chromatography | Downstream | Polishing | POL | 16 | 22 | 30 | Fixed | 2 | N | N | Y | Aggregate removal | Engineer input
13 | VF | Viral filtration (20 nm) | Downstream | Viral clearance | VF | 8 | 12 | 18 | Fixed | 2 | N | N | Y | Flux-dependent | Industry typical; replace with site data
14 | UFDF | UF/DF concentration + buffer exchange | Downstream | Formulation | UFDF | 14 | 18 | 26 | Fixed | 2 | N | N | Y |  | Industry typical; replace with site data
15 | FILL | Bulk DS filtration + fill / freeze | Downstream | Fill | FILL | 6 | 8 | 12 | Fixed | 3 | Y | N | Y | Weekday fill for QA release support | Industry typical; replace with site data
Note on G1: Min / Likely / Max hours feed the Monte Carlo (triangular distribution).
Note on J1: 'ProA cycles' = computed from Mass_Balance. Otherwise Fixed.
Note on M1: Critical steps get a staffing flag if they start on a weekend.

## Polishing_Options
Template | Step 1 | Step 2 | Step 3 | Description
A | POL-AEX | POL-CEX |  | AEX flow-through, then CEX bind/elute
B | POL-CEX | POL-HIC |  | CEX bind/elute, then HIC
C | POL-CEX | POL-AEX | POL-HIC | Three-step polishing

## Equipment
Equipment ID | Building | Equipment Type | Description | Working Volume L | Turnaround h | In Service | Notes
IN-A01 | Bldg-A | INOC | Inoculum lab (BSC + incubator slot) |  | 4 | Y
IN-A02 | Bldg-A | INOC | Inoculum lab (BSC + incubator slot) |  | 4 | Y
IN-A03 | Bldg-A | INOC | Inoculum lab (BSC + incubator slot) |  | 4 | Y
RK-A01 | Bldg-A | N3 | N-3 rocking bioreactor | 50 | 24 | Y
RK-A02 | Bldg-A | N3 | N-3 rocking bioreactor | 50 | 24 | Y
SB-A01 | Bldg-A | N2 | N-2 seed bioreactor | 500 | 36 | Y
SB-A02 | Bldg-A | N2 | N-2 seed bioreactor | 500 | 36 | Y
SB-A11 | Bldg-A | N1 | N-1 seed bioreactor | 4000 | 36 | Y
SB-A12 | Bldg-A | N1 | N-1 seed bioreactor | 4000 | 36 | Y
BR-A01 | Bldg-A | PROD | Production bioreactor | 20000 | 60 | Y
BR-A02 | Bldg-A | PROD | Production bioreactor | 20000 | 60 | Y
BR-A03 | Bldg-A | PROD | Production bioreactor | 20000 | 60 | Y
BR-A04 | Bldg-A | PROD | Production bioreactor | 20000 | 60 | Y
HV-A01 | Bldg-A | HARV | Disc-stack centrifuge + depth filter skid |  | 24 | Y
CP-A01 | Bldg-A | CAPT | Protein A skid + column |  | 12 | Y
VI-A01 | Bldg-A | VIN | VI / neutralization vessel |  | 8 | Y
DF-A01 | Bldg-A | FILT | Depth filtration skid |  | 6 | Y
PL-A01 | Bldg-A | POL | Polishing chromatography skid |  | 12 | Y
PL-A02 | Bldg-A | POL | Polishing chromatography skid |  | 12 | Y
VF-A01 | Bldg-A | VF | Viral filtration skid |  | 8 | Y
UF-A01 | Bldg-A | UFDF | UF/DF skid |  | 12 | Y
FL-A01 | Bldg-A | FILL | Bulk fill station |  | 8 | Y
IN-B01 | Bldg-B | INOC | Inoculum lab (BSC + incubator slot) |  | 4 | Y
IN-B02 | Bldg-B | INOC | Inoculum lab (BSC + incubator slot) |  | 4 | Y
IN-B03 | Bldg-B | INOC | Inoculum lab (BSC + incubator slot) |  | 4 | Y
RK-B01 | Bldg-B | N3 | N-3 rocking bioreactor | 50 | 24 | Y
RK-B02 | Bldg-B | N3 | N-3 rocking bioreactor | 50 | 24 | Y
SB-B01 | Bldg-B | N2 | N-2 seed bioreactor | 500 | 36 | Y
SB-B02 | Bldg-B | N2 | N-2 seed bioreactor | 500 | 36 | Y
SB-B11 | Bldg-B | N1 | N-1 seed bioreactor | 4000 | 36 | Y
SB-B12 | Bldg-B | N1 | N-1 seed bioreactor | 4000 | 36 | Y
BR-B01 | Bldg-B | PROD | Production bioreactor | 20000 | 60 | Y
BR-B02 | Bldg-B | PROD | Production bioreactor | 20000 | 60 | Y
BR-B03 | Bldg-B | PROD | Production bioreactor | 20000 | 60 | Y
BR-B04 | Bldg-B | PROD | Production bioreactor | 20000 | 60 | Y
HV-B01 | Bldg-B | HARV | Disc-stack centrifuge + depth filter skid |  | 24 | Y
CP-B01 | Bldg-B | CAPT | Protein A skid + column |  | 12 | Y
VI-B01 | Bldg-B | VIN | VI / neutralization vessel |  | 8 | Y
DF-B01 | Bldg-B | FILT | Depth filtration skid |  | 6 | Y
PL-B01 | Bldg-B | POL | Polishing chromatography skid |  | 12 | Y
PL-B02 | Bldg-B | POL | Polishing chromatography skid |  | 12 | Y
VF-B01 | Bldg-B | VF | Viral filtration skid |  | 8 | Y
UF-B01 | Bldg-B | UFDF | UF/DF skid |  | 12 | Y
FL-B01 | Bldg-B | FILL | Bulk fill station |  | 8 | Y
Note on F1: Cleaning, CIP/SIP, or changeover time after each use.

## Mass_Balance
Parameter | mAb-A | mAb-B | Unit | Source / Confidence
Working volume | 18500 | 18500 | L | Industry typical; replace with site data
Titer at harvest | 4 | 5.5 | g/L | Industry typical; replace with site data
Harvest yield | 0.92 | 0.92 | fraction | Industry typical; replace with site data
Protein A yield | 0.92 | 0.92 | fraction | Industry typical; replace with site data
VI + depth filtration yield | 0.97 | 0.97 | fraction | Industry typical; replace with site data
AEX yield | 0.95 | 0.95 | fraction | Industry typical; replace with site data
CEX yield | 0.88 | 0.88 | fraction | Industry typical; replace with site data
HIC yield | 0.85 | 0.85 | fraction | Industry typical; replace with site data
Viral filtration yield | 0.97 | 0.97 | fraction | Industry typical; replace with site data
UF/DF yield | 0.97 | 0.97 | fraction | Industry typical; replace with site data
Fill yield | 0.99 | 0.99 | fraction | Industry typical; replace with site data
Protein A column diameter | 160 | 160 | cm | Industry typical; replace with site data
Protein A bed height | 20 | 20 | cm | Industry typical; replace with site data
Protein A dynamic binding capacity | 45 | 45 | g/L resin | Industry typical; replace with site data
Protein A load factor | 0.8 | 0.8 | fraction of DBC | Industry typical; replace with site data
Protein A cycle time | 3.5 | 3.5 | h/cycle | Industry typical; replace with site data
Protein A setup + sanitization | 4 | 4 | h | Industry typical; replace with site data
Protein A duration spread | 0.15 | 0.15 | +/- fraction for Monte Carlo | Industry typical; replace with site data

## Campaign_Plan
Campaign ID | Building | Product | Client | Batches | First Thaw | Target Cadence d | Batch Prefix | QC Release d | Handoff to DP d | Notes
C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 10 | 2026-09-14 08:00 | 4.5 | A1 | 28 | 3 | Commercial campaign
C-B1 | Bldg-B | mAb-B | Client B (illustrative) | 8 | 2026-10-05 08:00 | 4.25 | B1 | 28 | 3 | High-titer process; Protein A is the pinch point
Note on E1: Batches, First Thaw and Target Cadence generate batches only when the campaign has no rows in Batch_List.
Note on I1: Days from bulk DS complete to QC release.
Note on J1: Days from QC release to DS available to Drug Product (freeze, storage, transfer).

## Batch_List
Batch ID | Campaign ID | Building | Product | Client | Planned Thaw | DP Need Date | Status | Bioreactor | QC Release d | Handoff to DP d | Notes
A1-01 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-09-14 08:00 | 2026-12-01 | Planned |  | 28 | 3
A1-02 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-09-18 20:00 | 2026-12-06 | Planned |  | 28 | 3
A1-03 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-09-23 08:00 | 2026-12-10 | Planned |  | 28 | 3
A1-04 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-09-27 20:00 | 2026-12-16 | Planned |  | 28 | 3
A1-05 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-10-02 08:00 | 2026-12-19 | Planned |  | 28 | 3
A1-06 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-10-06 20:00 | 2026-12-26 | Planned |  | 28 | 3
A1-07 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-10-11 08:00 | 2026-12-30 | Planned |  | 28 | 3
A1-08 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-10-15 20:00 | 2026-12-31 | Planned |  | 28 | 3
A1-09 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-10-20 08:00 | 2027-01-08 | Planned |  | 28 | 3
A1-10 | C-A1 | Bldg-A | mAb-A | Client A (illustrative) | 2026-10-24 20:00 | 2027-01-11 | Planned |  | 28 | 3
B1-01 | C-B1 | Bldg-B | mAb-B | Client B (illustrative) | 2026-10-05 08:00 | 2026-12-22 | Planned |  | 28 | 3
B1-02 | C-B1 | Bldg-B | mAb-B | Client B (illustrative) | 2026-10-09 14:00 | 2026-12-27 | Planned |  | 28 | 3
B1-03 | C-B1 | Bldg-B | mAb-B | Client B (illustrative) | 2026-10-13 20:00 | 2026-12-31 | Planned |  | 28 | 3
B1-04 | C-B1 | Bldg-B | mAb-B | Client B (illustrative) | 2026-10-18 02:00 | 2027-01-07 | Planned |  | 28 | 3
B1-05 | C-B1 | Bldg-B | mAb-B | Client B (illustrative) | 2026-10-22 08:00 | 2027-01-09 | Planned |  | 28 | 3
B1-06 | C-B1 | Bldg-B | mAb-B | Client B (illustrative) | 2026-10-26 14:00 | 2027-01-10 | Planned |  | 28 | 3
B1-07 | C-B1 | Bldg-B | mAb-B | Client B (illustrative) | 2026-10-30 20:00 | 2027-01-16 | Planned |  | 28 | 3
B1-08 | C-B1 | Bldg-B | mAb-B | Client B (illustrative) | 2026-11-04 02:00 | 2027-01-23 | Planned |  | 28 | 3
Note on F1: Requested thaw. Edit to move a batch. The app may schedule it later if equipment is busy.
Note on G1: Date Drug Product needs this lot released and available.
Note on H1: Planned, Hold (not scheduled) or Cancelled.
Note on I1: Optional. Pin the batch to one production bioreactor (e.g. BR-A02).

## Hold_Limits
After Step | Intermediate | Min Hold h | Max Hold h | Temperature | Basis
THAW | Shake flask culture (passage window) | 0 | 12 | 36.5 C | Passage window
N3 | N-3 culture (transfer window) | 0 | 12 | 36.5 C | Transfer window
N2 | N-2 culture (transfer window) | 0 | 12 | 36.5 C | Transfer window
N1 | N-1 culture (transfer window) | 0 | 8 | 36.5 C | Viable cell density window
PROD | Production culture (harvest window) | 0 | 36 | 36.5 C | Viability >= 70% at harvest
HARV | Clarified harvest | 0 | 120 | 2-8 C | Hold study (illustrative)
PROA | Protein A eluate | 0 | 72 | 2-8 C | Hold study (illustrative)
VI | Neutralized VI pool | 0 | 24 | RT | Hold study (illustrative)
VIDF | Filtered VI pool | 0 | 72 | 2-8 C | Hold study (illustrative)
POL-AEX | AEX pool | 0 | 72 | 2-8 C | Hold study (illustrative)
POL-CEX | CEX pool | 0 | 72 | 2-8 C | Hold study (illustrative)
POL-HIC | HIC pool | 0 | 72 | 2-8 C | Hold study (illustrative)
VF | Viral filtrate | 0 | 48 | 2-8 C | Hold study (illustrative)
UFDF | UF/DF retentate | 0 | 72 | 2-8 C | Hold study (illustrative)

## Flag_Rules
Rule ID | Severity | Rule | Threshold | Unit | Enabled
HOLD_BREACH | Red | Wait between steps exceeds the max hold | 100 | % of max hold | Y
HOLD_RISK | Yellow | Wait between steps uses most of the max hold | 75 | % of max hold | Y
DS_SLIP_YELLOW | Yellow | DS completion later than baseline plan | 24 | h | Y
DS_SLIP_RED | Red | DS completion later than baseline plan | 96 | h | Y
DP_NEED_MISS | Red | DS available to Drug Product after the DP Need Date | 0 | d | Y
DP_NEED_RISK | Yellow | DS available to Drug Product with less slack than this before the DP Need Date | 3 | d | Y
TRAIN_UTIL | Yellow | A downstream station is booked above this level in the next 7 days | 90 | % | Y
WEEKEND_CRITICAL | Yellow | A critical step starts on a weekend or holiday | 1 | flag | Y
CREW_OVER | Yellow | Operators needed in a 12 h shift exceed crew | 100 | % of crew | Y
MATERIAL_SHORT | Red | Stock runs out before reorder lead time can cover it | 0 |  | Y
MATERIAL_LOW | Yellow | Stock runs out within the campaign; order now | 0 |  | Y
BATCH_LOST | Red | Batch terminated | 0 |  | Y
EQUIP_DOWN | Red | Equipment down or out of service (red if it delays work or leaves no capacity, else yellow) | 14 | days ahead | Y

## Resources
Building | Area | Operators per Shift | Shift Length h | Pattern | Notes
Bldg-A | Upstream | 6 | 12 | 4-crew 2-2-3 | Seed + production
Bldg-A | Downstream | 8 | 12 | 4-crew 2-2-3 | Harvest through fill
Bldg-B | Upstream | 6 | 12 | 4-crew 2-2-3 | Seed + production
Bldg-B | Downstream | 7 | 12 | 4-crew 2-2-3 | Ramping; one open requisition

## Materials
Item | Building | Consumed at Step | On Hand | Use per Batch | Unit | Lead Time d | Refill To | Notes
Protein A resin life | Bldg-A | PROA | 60 | ProA cycles | cycles remaining | 70 | 200 | Column packed 2026-06; 200-cycle limit
Protein A resin life | Bldg-B | PROA | 35 | ProA cycles | cycles remaining | 70 | 200 | Re-pack needs ~36 h capture downtime
Virus filter, 20 nm | Bldg-A | VF | 26 | 4 | m2 | 56
Virus filter, 20 nm | Bldg-B | VF | 40 | 5 | m2 | 56
Harvest depth filter set | Bldg-A | HARV | 12 | 1 | sets | 28
Harvest depth filter set | Bldg-B | HARV | 6 | 1 | sets | 28 |  | Supplier allocation
Production media lot | Bldg-A | PROD | 10 | 1 | batches | 21
Production media lot | Bldg-B | PROD | 8 | 1 | batches | 21
Note on E1: Number, or 'ProA cycles' to use the computed cycle count per batch.
Note on H1: Stock after a replenishment. For resin: cycles available after a planned re-pack (an Equipment down event or decision whose note says re-pack).

## Calendar
Date | Holiday
2026-11-26 | Thanksgiving
2026-11-27 | Day after Thanksgiving
2026-12-24 | Christmas Eve
2026-12-25 | Christmas
2026-12-31 | New Year's Eve
2027-01-01 | New Year's Day

## Events
Event ID | Active | Building | Batch | Step ID | Equipment ID | Type | Hours | Start | Logged By | Note
EV-001 | N | Bldg-A |  |  | HV-A01 | Equipment down | 48 | 2026-11-19 06:00 | Shift lead | Centrifuge bowl seal failure; vendor on site Thursday
EV-002 | N | Bldg-B | B1-03 | HARV |  | Delay | 16 |  | Shift lead | Desludge fault; harvest restarted
EV-003 | N | Bldg-B | B1-05 | PROD |  | Batch lost | 0 |  | Upstream lead | Contamination detected (illustrative)
Note on G1: Delay: adds hours to a step. Equipment down: unit unavailable from Start for Hours. Batch lost: batch ends at the step. Hold extension: adds hours to the max hold after Step ID (requires approved data).